## Slide 1: Major activities
Activity | Indicative timeline
Inception phase – identification of key stakeholders and Inception Report | Oct-Dec 2023
Establishment of Steering Committee and Working Group | Dec 2023
Individual meetings with national stakeholder groups in each country and needs assessments | March 2024
Technical reviews of existing standards | Jun-Sep 2024
Stakeholder consultation workshop on review of standards (Tashkent) | Oct-Nov 2024
Develop a system to improve design standards and produce draft regional standard | Nov 2024-Mar 2025
Finalize regional standard and presentation | May 2025
Develop accompanying training modules | Jan-May 2025
Deliver training for stakeholders and train-the-trainer sessions (online) | Apr 2025
Final Safer Road Infrastructure Workshop (Tashkent) | May-June 2025